## Cover Page
Clinical Safety Hazard Log - GP Connect
Programme | GP Connect Programme | Document Record ID Key
Sub-Prog / Project | Clinical Safety | GPC-HL-001
Prog. Director | Richard Phillips | Status | Draft
Owner | Cath Johnson | Version | 0.4
Author | Cath Johnson | Version Date | 2020-04-16
Clinical Safety Hazard Log - GP Connect
Document Purpose
This hazard log identifies potential clinical hazards that could occur when using GP Connect functionality through a consumer system. Please consider whether any of the hazards could apply to the way you are going to use the system. If necessary, take mitigating action to ensure the solution you are using is safe.
Copyright © 2020, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre. All Rights Reserved.

## Version History
Amendment History
Version | Date | Amendment History
0.1 | 2020-02-18 | First draft Hazard Log
0.2 | 2020-03-11 | Added new hazards: 13 and 14. Updated 16.
0.3 | 2020-04-06 | Added new hazards: 23,24,28 and 33. Updated 50.
0.4 | 2020-04-16 | Inclusion of Hazard 12 and addition of suggested actions
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
|  | GP Connect Clinical Safety Team | 2020-04-16 | 0.4
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Cath Johnson |  | Clinical Lead and Clinical Safety Officer | 2020-04-06 | 0.3
Distribution
GP Connect Clinical Safety Personnel
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## Hazard Log
Hazard number | Hazard type | Hazard name+C:D+C:D | Hazard description | Potential clinical impact | Possible causes | Suggested actions to reduce hazard
1 | Medicines and Allergies Structured | Lack of detail in externally entered information (out of hours) | Externally entered medication information is not as detailed as internally entered medication - for example, the name of a prescriber from an out of hours provider may be included, but not the name of the prescriber's organisation. This information is not present in the message for medications prescribed away from the GP practice, but entered on the GP practice system. | This could impact on the ease of contacting the original prescriber in case of queries or in the event of a significant incident occurring. | The providers do not have a defined value set to use to enable standardisation of information. | The use of FHIR profiles by provider systems that provide detailed value sets. Export textual information to support the message - provider system should prompt for more detail. | List
2 | Medicines and Allergies Structured | Inconsistencies on the coding of allergies | Allergy causative agents in GP systems are not standard and are unable to be processed by a machine - for example, coded and free text entries. Different suppliers use different coding systems some of which are proprietary to that particular system. It will be impossible for consuming systems to trigger decision support systems from the coding systems that GP suppliers currently use. This is because the allergy may be coded in a way that the consuming system doesn't understand. Consequently, clinicians have to manually enter the code as free text. | Patient is prescribed/administered incorrect medication which could cause harm, trigger an allergy or worsen a clinical condition. It will be impossible for consuming systems to trigger decision support systems from the coding systems that GP suppliers currently use. | The GP systems have not implemented the agreed SNOMED causative agent list which is published in TRUD. This results in: 1. Inaccuracies in some of the data mapping. 2. Local code in specific GP systems. 3. Human error in cross-mapping. 4. Coded/Uncoded Allergies. | The system should degrade (provide more detail about) the allergy and present the degrade code and text to the user to resolve.
7 | Medicines and Allergies Structured | Shared data risk when exporting meds and allergies | When an allergy is shared into a GP practice from a community organisation, the shared allergy triggers decision support locally in the GP practice, but is not exported via GP Connect. Any decision support system in the consuming system is not triggered. | The clinician may not have the correct, up to date information to provide safe and effective care. | GP Connect only shares the GP element of the patient record. | Review implementation guidance (Access Record HTML and structured). Consider using a warning message to highlight the issue to the end user.
12 | Structured Immunisations | Planned vaccination did not happen | The manner in which the planned vaccination not given is communicated via FHIR is misinterpreted or misrepresented by the consumer or additional third party system. | A clinician might believe that a vaccination has been given when in fact it hasn’t, or has been given twice. The clinician might interpret incorrect information and come to a possible incorrect diagnosis. Preventative healthcare might not be given. | The use of the 'Given' procedure code and modifier for 'not given vaccinations in the FHIR model results in one of the following: • The inclusion in the consumer system of the modified given procedure is not correctly interpreted by the user. • The given procedure code and modifier are separated in some areas of the system - therefore misrepresenting the vaccination information. • Automated reporting or processing doesn't recognise the modifier. • The consuming system utilises the conversion of the given procedure to a 'not done' procedure, but the conversion fails resulting in the given procedure being entered into the record (edge case). • Inconsistent use of FIHR resources could increase the likelihood of misunderstanding.
13 | Structured Immunisations | Multicomponent vaccines | Having different ways to represent components within a vaccine can cause a clinical hazard. The same information can be recorded in different ways - for example, a measles vaccination was recorded, but a full measles, mumps and rubella vaccination was actually given to the patient. | This information can be misinterpreted when scheduling the next vaccination, which may lead to under- or over-vaccination. | Vaccines may be entered in different ways by the clinician within the system. | Consuming system needs to be aware that some of the time a single vaccine recorded may have been part of multicomponent vaccine. The end user should review vaccine information recorded at the same date as the single vaccine entry.
14 | Structured Immunisations | Prescribed vaccines | Prescribing vaccines (as a drug) won't be shown in the immunisation section. For example, cholera is a travel vaccine but would not be recorded in the immunisation profile as it is prescribed in the medications section and the patient takes the medication at home. Influenza vaccine can also be prescribed and found in the medications section, but not in the vaccination section. | A clinician may be unaware of the correct immunisation status of the patient. There is a potential for over-immunisation of the patient. Perception that a patient is at increased risk of a disease that they have been previously vaccinated against. Clinician may erroneously think they have a full list of immunisations if any are seen in the medications profile. | Prescribing vaccines can be recorded in different sections of GP IT systems. | Medications profile should be called with the vaccine profile if appropriate.
11 | General Risk | Consuming system misunderstands detail for data sent from providing systems | The data held in GP systems can be complex and detailed. There is a risk that consuming systems could misunderstand data that they receive. | If the consuming system is not designed in a way that fully considers the detail of the data, then it may not display it to the clinician in a way that is clear and appropriate. | Examples: 1. The structure of the investigations data returned by GP Connect is complex. It can contain comments against different levels of the report. 2. GP Connect 'allows' a consumer of data to request the medications without all the issues. | Consumers should have availability to rich data to clinically assure against. The test data will be designed to work in tandem with the specification.
16 | General Structured | Modular design of GP Connect profiles | Profiles can be requested separately in Access Record Structured. This gives flexibility for consuming systems and enables bespoke development to provide an efficient and effective product for the end user. However, there is a risk that the consuming system may not pull in all the information necessary for safe and effective patient care - for example, it may call the medicines profile but not the allergies one. | Missing information may lead to possible incorrect diagnosis and treatment. | Requesting the wrong levels of detail for medications. Requesting the inappropriate 'clinical area' (logical sections of GP systems) - for example, requesting medications without allergies. | The specification clearly describes how the GP record has been logically modelled within GP Connect. The way in which the different clinical areas interconnect is described in detail to ensure clinical safety. The way searches work has been modelled to provide developers with the safest level of detail first. For example, medications will always be returned with all the issues unless a developer codes specifically for less data to be returned.
17 | Structured Uncategorised Data | Clinically significant information not highlighted and missed | Uncategorised data might not be displayed where the clinician is expecting it to be displayed. Information that should be recorded under a different profile is returned in the uncategorised data only. Clinically relevant information that should be recorded in uncategorised data is not easily accessible due to existing alongside large amounts of less relevant information. | Clinically significant information not highlighted and missed. This compounds source data consistency issues in GP records - for example, on child protection register, system flags through decision support, receiving system doesn't have decision support triggered by the same rules and information gets buried. | Items in GP records not being flagged as problems. Variance between systems and practices in the way they record data - for example, referrals are added as a note (free text) or a code in the journal. | The GP Connect specification limits the ability to partition uncategorised data. This more closely resembles the way information is seen in the GP records. Standalone free text is not available in the uncategorised profile. Ensure that information in the appropriate modules or parts of the GP clinical system end up in the intended profile and not in uncategorised data - and vice versa. Business change documentation needs to strongly highlight this. |  | List
18 | General Structured | Data without context can be misinterpreted | Uncategorised data seen in isolation from associated categorised data could be incorrectly interpreted. | The clinician may interpret incorrect information to come to a possible incorrect conclusion. | Requesting uncategorised data where linked data is not displayed. Consumers don’t know how to display this data to their users or users don’t understand the types of information displayed in this category. Examples: 1. Free text is used to indicate whether the patient is lying down, sitting or standing during a blood pressure reading. Code: Blood pressure 140/80 Text: lying down Code: Blood pressure 160/90 Text: sitting 2. Free text is used to indicate the three separate readings of a patient's peak flow test (asthma). Code: Peak Flow Text: Reading 1 540 Reading 2 560 Reading 3 550 | Consumer needs to make their users aware that tightly bound text will be returned with codes and any other text needs to be retained by requesting consultations. Where uncategorised data links to problems and consultations, consuming systems should make users aware, where it is relevant. Testing using templates to ensure to free text is linked to relevant codes.
19 | General Structured | Risk of duplication due to sharing | If a consumer is trying to import structured data from GP Connect there is a risk that some of the data may already be in that system and this might cause duplication. | The clinician may interpret incorrect information to come to a possible incorrect conclusion | Consuming system makes a similar call to GP Connect as it has previously - for example, meds reconciliation after more than one hospital admission. | We have specified an ID that will be persisted for each individual FHIR resource (e.g. medication request or observation) exported by provider systems. Consuming systems are advised to use this to prevent duplication. It is still possible, currently, that items moving between systems via legacy systems or data migrations will not persist these IDs so consuming systems are advised to code defensively in such a way as to highlight similar data items before import. Consumers are advised to test the use of these individual FHIR IDs.
23 | Structured Pathology | Structured test results: Pathology | Within the test result section of the pathology specification there is a risk that an interim test result is returned and the clinician believes it is the final report. For example, with fungal nail clippings the lab provides an interim report and then a final report 3 weeks later. | Clinician potentially diagnoses a patient incorrectly. Clinicians from other care settings may not be familiar with interim reports. | Doesn’t come with metadata with status. Status is part of the textual report. | Ensure all text is displayed to the user from Edifact messages. Test that all the text is displayed to the end user in the message in the same format that it was sent in Edifact. Users need to be aware of Edifact and the way messages are sent.
24 | Structured Pathology | Structured - Naming conventions | Labs don’t have a unified test list and use different equipment and reagents. There are also different ways to undertake procedures. There is no central coordination. | Clinical mis-interpretation - lab tests are different compared to other systems which are more homogenous. | There is no national laboratory standard. | National pathology project is defining and developing unified test list. GP Connect is designed in such a way that the message will send any type of test, including where anything within the pathology bounded code list can be sent (agnostic of type of tests). It is designed to preserve text formatting as it was sent in the Edifact message. Test that all the text comes through in the message in the same format that was sent in Edifact.
28 | Structured Pathology | Loss of consultation structure | If the structure contained in the consultation is not maintained then some of the overall meaning of the consultation may be lost. All of the information in a consultations is recorded at a point in time and context may be lost if not all of the information is transported together. | Clinicians won't find the information they need in the places they expect. | Different consultation structures in different systems. | Consumers should test that all consultation headings are maintained and items and text remains in the same order.
31 | General Structured | Local warnings not currently shared in GP Connect | Local warnings that may have been added at the patient's registered practice may not be shared via GP Connect - for example, patient has previously been abusive with reception staff. | The clinician may not have access to essential information that may affect the care and communication with the patient. | Not been covered as part of phase1 of GP Connect. | Consumers should be aware that the sharing of local warnings is not currently in scope.
32 | General Structured | Data marked as private is not shared | Data marked as private is not shared via GP Connect. | The clinician may not have access to important information that may affect the care of the patient. | Privacy for patients | The provider system should ensure a warning code is added if information is missing. The consuming system should display the warning.
33 | General Structured | Misunderstanding that consultations do not represent the whole patient record (have not defined how to request the whole record) | If a subset of the record is requested the clinician may not be aware that the rest of the record is available. | The clinician may not have a full picture of the previous care of the patient. | Poor consumer system design | The provider system should ensure all information is sent as a design principle. Restrictions on queries to minimise risk of incomplete information. Consumer should ensure understanding of the implementation guidance. Test the principles of ensuring all information received, design all queries so that they understand the information coming from it and are aware of any gaps for their users.
36 | General Risk | Technical issues delaying sharing of information | Patient diagnosis or treatment is delayed because some of the patient data is not available as a result of technical issues. | The clinician may not realise that the whole record is not being displayed. If this is the case any decisions the clinician has to make could be potentially unsafe - for example, if they prescribed medication that interacts with another drug that was recently prescribed, but was not part of the record returned. The clinician may not realise that the whole record is not being displayed. If this is the case any decisions the clinician has to make could be potentially unsafe. For example, medication is prescribed that interacts with another drug which was recently prescribed but was not part of the record returned. | The providing system fails to provide all of the relevant data for the API call. There may be some loss of data in the transit from the provider to the consumer. The consuming solution may not correctly display all the information contained in the message. The consuming system interprets data in an inconsistent or incomplete way across all providing systems | The specification requires the provider system to ensure that the data is provided in sections so it is easier to tell if areas are missing. Consumer systems should test and retain evidence against all providers whose data they are consuming.
37 | Medicines and Allergies Structured | Medicines taken by the patient but not prescribed or provided by the GP practice | The record that is pulled through from the GP system does not contain the whole prescribing record as not all of the drugs the patient is taking are in the GP record. | Patient is prescribed/administered incorrect medication which could cause harm, trigger an allergy or worsen a clinical condition. System misleads a user into prescribing/administering an incorrect medication due to incomplete medication record on the GP system. Incorrect diagnosis or treatment if the information was not validated against other sources of information. | The complete medication history is not held on the GP clinical system. Any of these scenarios could result in an incomplete drugs history, for example: 1. Drugs obtained through private care. 2. Drugs purchased privately by patient, for example, over the counter. 3. Drugs prescribed in sexual health clinics, prisons and military settings, and so on. 4. Controlled Drugs (Schedule 2/3) 5. Incorrect date/dose/frequency, missing medications/variable doses. | GP Connect specification includes how and what types of medications, including prescribed elsewhere medications, are to be displayed on the API. Consumer systems should test and retain evidence against all providers whose data they are consuming.
38 | General Risk | Patient data is missing from the patient record in the GP system due to non-technical issues | Although GP patient records have the best consolidated view of the patient's medical history, there will always be gaps. | The clinician may not realise that the complete patient history is not being displayed. If this is the case any decisions the clinician has to make could be potentially unsafe. Some examples include: 1. System misleads a user into prescribing/administering an incorrect medication due to incomplete allergy/adverse reaction record on the GP system. 2. Patient is prescribed/administered incorrect medication whilst could cause deleterious effects, trigger an allergy or worsen a clinical condition. | This is a general scenario in which the GP isn't aware of the patient's full medical history. | Guidance in the specification and Clinical Safety Officer guidance highlights this issue.
40 | General risk | Out of date patient data may cause an incorrect diagnosis with subsequent delay or incorrect treatment as a result of technical issues | There are a number of failure modes of the end to end transaction that could result in the consumer receiving an incorrect or out of date GP record. | The clinician may not realise that an incorrect or out of date record is being displayed. If this is the case any decisions the clinician has to make could be potentially unsafe. For example, an inactive record for the patient is sent which may not be up to date if the patient has had any change since their record was last updated at the GP practice. This could include that a patient has been seen in another setting and had medications prescribed or had additional clinical notes added. | There may be many possible causes, including incorrect population of the message, not doing a PDS trace and accessing an out of date record, retrieving a wrong patient, etc. Examples: 1. The consuming solution has the responsibility to do a 'timely' PDS trace on the patient prior to sending the request. However, as this can include DBS batch tracing this may not be fully up to date. These could be 'edge cases', where a record is transitioning GP practices or a patient has died and that has not yet been updated. 2. When a practice switches supplier there is a period of time when the information in the current clinical system and the target clinical system may be out of date due to current work-arounds that practices put in place during a switch. | Commissioning/consuming organisations should test and retain evidence against all providers whose data they are consuming.
42 | General Risk | Patient chooses to not share some or all data outside the practice | GP Connect will not provide data where a patient has said they do not want to share their data outside of their GP practice or back to the registered practice in a federated clinic appointment scenario. GP Connect has no ability for a clinician to override this decision. Examples of clinical scenarios: 1. In A&E where the patient is asked to share data and changes their mind or where the patient is unconscious and there is a medical imperative the clinician does not have any power of override or patient seeking drugs of abuse does not want the contact and the prescription reported to the practice. This would currently not be visible to the practice in any way. 2. A sibling posing as the patient (knowing name, address, date of birth) and seeking medication. If part or all of the record isn't shared incorrect decisions can be made. | Patient diagnosis or treatment delayed. GP Connect is using the same model as SCR in that data will not be sent if the patient has recorded a dissent to share. This may lead to clinical safety issues which could have been avoided, for example, medication is prescribed to which the patient is allergic, has contraindications or a drug interaction. | This is a known outcome of the patient dissenting to share their data for the purposes of shared care in a direct care setting. | The option for a patient to dissent to their data being shared is a requirement of the developing local and national data sharing models and as such has been specifically designed in to provide this option. The result of the patient exercising this option is that they expose themselves to this risk which they have to accept. Consumers should review this area in the development of their system.
43 | General Risk | All of a patient's data is unavailable as a result of technical issues | There are a number of failure modes of the end to end transaction that could result in the consumer not receiving all of the GP record. For example, there is likely to be some downtime for GP Connect when a GP practice changes system provider. A new GP Connect endpoint cannot be set up at a provider until the old one is removed as the Spine will not know which is live when receiving a consumer request. | Patient diagnosis or treatment delayed due to clinician having to make decisions without the patient record being available. This may lead to clinical safety issues which could have been avoided, for example, medication is prescribed to which the patient is allergic, has contraindications or a drug interaction. | Any technical fault that prevents the end to end process succeeding. Examples: 1. If a number of messages fail and need to be resent then there is no technical mechanism to resend all messages. 2. When a practice switches supplier there is a period of time when the practice will lose GP Connect connectivity. This is due to the change in ASID that takes place when a practice switches supplier. As the SSP validates the ASID to allow transactions, when a practice gets a new ASID due to a supplier switch they are then rejected by the SSP. | Business continuity plans should be put in place and implemented to mitigate any technical faults. For example, when changing providers the following actions must be taken: final day on old system, when they shut down old supplier removes GP Connect endpoint as soon as that is removed new supplier adds GP Connect endpoint and overnight polls harvest the SDS data following morning the data sharing file is created and loaded into the Spine before the start of business
45 | General Risk | Medication not prescribed by a GP practice clinician but within the GP record is not retrieved or it is not known where they were prescribed | Medications that are not prescribed by a GP practice clinician are not presented to consuming clinicians, i.e., medications recorded on GP systems does not get sent to GP Connect API. 1. Drugs that are prescribed elsewhere that are referred to in the GP record in a section that is not the medication statement 2. Drugs that are detailed in the Medication statement. Knowing these have been prescribed elsewhere is implied as there is no matching medication order. These would mean there is not a complete medication record for the receiving clinician to know all medication and who prescribed it. | Clinician makes incorrect assumptions about what the patient is currently taking. Patient is prescribed/administered incorrect medication whilst could cause deleterious effects, trigger an allergy or worsen a clinical condition. | Examples: 1. The medication statement profile will not pick up medication detail from other areas of the GP record that are not referenced or coded so it is not possible to send this data or to mitigate. 2. The drug is in the medication statement but the origin of who prescribed the drug is not captured in the GP record, due to the data not being correctly entered or to system limitations, which means this data cannot be sent in the API. 3. The drug is in the medication statement and the origin of who prescribed the drug is not captured in the GP record in a format or code that can currently be utilised in the API. | GP Connect specification includes how and what types of medications are to be displayed on the API. Consumer clinical validation assurance necessary to ensure that the API behaves in the manner expected by the user.
46 | Medicines and Allergies Structured | Date/time stamp of retrieval of medication/record from GP system is not presented to the end user of the data | Where a consuming solution may import the structured data direct into a local solution and then persist or cache that data received from a GP system it is not clear what date and time the information was retrieved from the patient's record. The clinician does not know that this is not 'real time' data and therefore does not check that the medication information is still current and correct. | Clinician makes incorrect assumptions about what the patient is currently taking. If the patient is being seen as an outpatient they may have had a subsequent medication changed or prescribed which is not noted in the record that is persisted in the patient record. | The GP system does not send this information. This is known by the consuming solution from date and time information captured for audit and should be used to generate an entry and display in its solution. If this does not happen and the requirement to retrieve new data is not automated when a patient record is accessed in the consuming system the up to date information may not be displayed to the clinician. | Consuming solution must display the date/time when the data was captured from the GP system. It is the responsibility of the consuming system to clinically assure this risk.
48 | Medicines and Allergies Structured | Potential for duplication of data | Where integrating records, there is a risk of duplication where data with no unique identifiers has been retrieved previously. | Potential for the patient record to become cluttered making treatment and decision making more difficult and changes are less apparent. | Insufficient validation and filtering at the points that structured data is imported and merged in clinical systems. | The specification mandates unique identifiers for individual resources to assist in de-duplication. Clinical validation assurance to ensure that the API behaves in the manner expected by the user.
50 | Medicines and Allergies Structured | Unable to distinguish if a repeat medication is current or not | Clinicians cannot establish how long ago repeat medications have been prescribed on a patient's record. Clinicians cannot establish whether a repeat medication is still being taken by a patient or not. | Clinician makes incorrect assumptions about what the patient is currently taking. Clinician cannot be confident that they have the patient's full list of repeat medication that is currently being taken and when it was last issued. Patient is prescribed/administered incorrect medication whilst could cause deleterious effects, trigger an allergy or worsen a clinical condition. | GP system does not send the date on which the prescription was last issued. As a result, for a prescription that is on a repeat and has no issues remaining it is difficult to know if it is still being taken. Not all GP systems have the same process; for one GP system, when all issues have been used, the medication is no longer current and therefore is discontinued without clinician intervention. | A repeat medication section should include an historic element. This is critical so that the clinician has a clear view of medications that will still be being taken by the patient but are past their issue end date. In primary care, a minimum of 3 months but more usually 12 months should be considered.
51 | Medicines and Allergies Structured | Source of medication data is unclear | Where a consuming solution has imported structured data, it may not be clear in the local solution that the data was retrieved from a GP practice. | Clinician makes incorrect assumptions about the origin of the patient's medication. | The consuming solution has requested the information from GP Connect and has not advised the end user of the source of the information. This is known by the consuming solution and should be used to generate an entry, and display in its solution that the data was retrieved from the patient's GP record. | GP Connect specification includes that the source of information is entered in the API - for example, author and practice details. It is the responsibility of the consuming system to clinically assure this risk.
52 | General Structured | Difference in rendering/presentation due to FHIR® standards framework mapping | Clinical context/meaning may be lost when the consumer creates their own render which is different from sender’s render - for example, the order of the document headings or the presentation of clinical content within each heading may vary between sender and consumer, and not be standardised across care settings. | This may lead to important clinical information being displayed incorrectly, which may cause delay to the assessment/treatment of the patient, and potentially inappropriate care. | Sending systems are not able to share their style sheet with consuming systems. No formally agreed default clinical presentation/user interface for displaying headings/content. | As per the Professional Record Standards Body (PRSB) implementation guidance: 1. The order in which headings appear can be agreed locally. 2. At minimum the composition has PRSB headings for default view, although it doesn't define any style guide on how the content should be displayed. 3. When headings are displayed, the first letter of the first word should be capitalised. It is recommended that, as per the Accessible Information Standard Implementation Guidance document for printed communication, a minimum font size of 12 point, preferably 14 is used with a clear, uncluttered and sans serif font such as Arial. All headings should be displayed using the same font size and font face - for example, Arial.
General Risk
General Structured
Medicines and Allergies Structured
Structured Immunisations
Structured Pathology
|  | Structured Uncategorised Data | Top
Go to Formulas > Name Manager